2017 ARIAS·U.S. Spring Conference

Ritz-Carlton Naples, FL

May 3 – 5, 2017

Conference Development Timeline - Conference Co-Chairs

General Timeline

Dec 2016 – Jan 2017 	Co-Chairs discuss conference planning process (Review previous conference evaluations, tentative timeline, and preliminary timed agenda, sequencing of sessions, rough out faculty, contact faculty

December 11, 2016	Finalize sponsorship prospectus

December 16, 2016	Finalize call for proposal process

December 19, 2016 		Call for proposal opens

January 9	Save-the-date content due from conference co-chairs

Staff provides theme and text for save-the-date card to Creative Dept.

January 16	Call for proposal closes

January 23 – 30	Save-the-date card – mailing

February 6 	Registration opens on website / Email communication goes out to ARIAS database with save the date and open registration link

February 9 	Brochure – Provide draft text to Creative for announcement brochure, including Co-Chair letter, schedule, confirmed faculty names, registration information & form, info about the Ritz-Carlton and surrounding area

February 22	Post and email conference brochure

March 3	Mail out Conference brochure (use same mailing list as ‘save the date’ list / email brochure, deadline reminders and links

March 20	Early bird deadline and full refund cancellation deadline / Run report of those not registered for marketing purposes

March 30			All remaining content for Conference Program due to Creative

March 30			Submit materials for CLE processing (IL & PA)

April 7				Hotel room block deadline

April 19				Email registrants link to conference program & materials

April 24				Regular registration deadline

April 25				Shipment date

April 27	Finalize conference evaluation in survey monkey / Finalize onsite rolling slide deck (Runs during meal times and breaks)

May 3- 5			Spring Conference

Co-Chair Timeline

January 18 – 20	Planning committee reviews submitted proposals independently

Jan 23 – Feb 3	Proposal selections /agenda development/ Co-Chairs finalize agenda and speakers

February 6 – 24	Co-chairs reach out to session panels to discuss session focus and direction in more detail

Feb 3 – 8	Data Security workshop call to discuss logistics

February 8	 Co-chair announcement letter for brochure due

February 	Webinar/Conference call with round table speakers

Feb 20 –24 (week of) 	Planning call

March 6 – 17 (week of)	Planning call

March 21 	Co-chairs receive post early bird deadline registration numbers

March 23			Co-chair welcome letter for conference program due

April 10- 17 (week of)		Planning call

April 21	Finalize co-chair run of show document (conference timeline that includes assns. of speaker introductions and staff, announcements, session times/breaks and special notes)

Speaker Timeline

February 3	All proposal submission contacts notified / Speaker management - All speakers notified of session times and deadlines (bios/headshots /materials/AV requirements/PPTs)

February 8	Speaker confirmation deadline

March 20			Speaker Registration deadline

March 23			Speaker session materials and AV requirements deadline

March 28			Speaker session materials extension and AV requirements deadline

April 24	Speaker PowerPoint presentations due